## Sheet1
Number | Description | Status | Tested
1 | Remove 'already registered' error message when email address is changed/corrected | Leave | N/A
2 | After positive account creation message, wait 3-5 secs and then divert back to log in screen | Complete | OK
3 | Forgot password link ; Reset it Here, change to reset it here | Complete | OK
4 | Log In, Forgot password and Register dialog boxes all have different font weight, colour and sizes. Make them universal (like Log in page) | Complete | OK
5 | Reset password has error Incorrect integer value: '' for column 'userID' at row 1. | Complete | OK
6 | Add an Event Log to log all log-ins and changes | Partial
7 | Change of sex (selecting female) in user profile not working | Open
8 | Edit device reallocated device to different customer | Open
9 | Vehicle lookup not working on edit device (it was) | Open
10 | Installs coming up alerts Date Format is YYYY-MM-DD | Complete | OK
11 | Dismissing alerts no longer works | Complete | OK
12 | Customer select box is hidden by overflowing menu | Open
13 | Condensed/hamburger menu is not vertical | Open
14 | Change Password option | Open
15 | If logged out, ensure allpages return user to log in page | Open
16 | Need to add filters to event log page | Open
17 | Event log should record adding new customer | Complete | For Test
18 | Event log should record adding new customer contact | Open
19 | Event log should record deleting customer | Open
20 | Event log should record deleting customer contact | Open
21 | Impending renewals due in '1 days' should read 1 day | Complete | OK
22 | Event log should record adding new insurer | Complete | For Test
23 | Add Broker gives an SQL error UserID invalid value | Open
24 | Need option to add new Device
Need option to add device status description
Need option to add footage status description
Need option to add installer to installer list
Need option to add SIM status description
Need option to add supplier to supplier list

## Modules
Renewal Type?????
Select Type
CONTACTS
Search
Delete
CUSTOMER NOTES
Search
Delete
DEVICES
Add
Edit
Delete
Rerassign
FOOTAGE
Add
Edit
REPORTS
GLOBAL SETTINGS
EVENT LOG
YOUR ACCOUNT